Resolution amending Resolution 13, effective 1/29/2009, entitled "Providing for an Agreement or Agreements, or use of existing Agreements and/or a Contract or Contracts, or use of existing Contracts, and for the purchase of materials, supplies, equipment, and/or services for various projects in connection with the Neighborhood Needs Program in Council District 8; and providing for the payment of the costs thereof by adding $9,000 for Traffic Study-Inner City Transit Options," to extend the timeframe outlined in Section 2 for the issuance of a Request for Proposal.

Be it resolved that the Council of the City of Pittsburgh hereby enacts as follows:

Section 1.	That Section 2 of Resolution 13, effective 1/29/09, is hereby amended as follows:

Section 2.   The  Director of City Planning is directed to issue a Request for Proposals relating to line item “Traffic Study – Inner City Transit Options” before February March 1, 2009, with specific criteria, reporting and scheduling outlined in Exhibit A.

EXHIBIT A

PROBLEM STATEMENT

Purpose and Needs

Project Goals

DATA COLLECTION AND FIELD INVESTIGATIONS:

Fieldview of CSX/AVRR and Other Rail facilities

CSX/AVRR Operations and Schedule Analysis

Other Railline Operations and Schedule Analysis

Review and Analysis of Existing Documents and Studies

EXISTING CONDITIONS ANALYSIS

Data Search and Analysis on DMU commuter rail systems and this line

Data Search and Analysis on Public-Private partnerships for similar transit systems

Data Search and Analysis on creation of parking garages for revenue

New Internet Search and Analysis of viability of the project

EVALUATION CRITERIA

Consistency with Regional (SPC) goals

Land Use and Mobility

Feasibility and Cost Effectiveness

Potential and Available Funding Sources

Transportation and Traffic Impacts

Environmental and Engineering Impacts

Community and Stakeholder Support - 2 Community Meetings

Project Planning and Implementation

DRAFT AND FINAL REPORT PREPARATION

Prepare Draft Report Narrative

Present Draft Report to City Council during Post Agenda

QAQC

Review Commentary from Councilman Peduto gathered from Council and Community

Prepare Final Report Narrative

SCHEDULE

RFP to be issued by the Director of Planning no later than February March 1, 2009

Selection of a Firm to be decided no later than March Apri1, 2009

Field study to begin March April 2009

First Community Meeting to be held April May 2009

Second Community Meeting to be held May June 2009

Draft Report presented to Council June July 2009

Final Report presented to City Council no later than August September 1, 2009